## Sheet1
Task | Date | Baseline Estimate | Start | End | Interruptions | Measured time (Hours) | Percentage | Adjusted estimate
Setting up project - double jump, adding rigidbody etc | 2021-02-16 | 0.05 | 11:30 | 11:35
Writing code for double jump | 2021-02-16 | 1.5 | 11:45 | 13:17 |  | 1.37
Setting up project - movement and camera follow | 2021-02-23 | 0.1 | 13:30 | 13:45 | 0.05 | 0.15
Writing camera follow code | 2021-02-23 | 0.2 | 13:50 | 14:05 |  | 0.15
Writing Player Movement code | 2021-02-23 | 0.4 | 14:02 | 14:46 |  | 0.44
Setting project - pick up | 2021-03-02 | 0.05 | 13:10 | 13:13 |  | 0.03
adding rigidbody to player and adding movement code | 2021-03-02 | 0.3 | 13:14 | 13:48 | 0.04 | 0.34
fixing broken script | 2021-03-02 | 0.15 | 13:50 | 14:20 |  | 0.3
Pick Up script | 2021-03-02 | 0.35 | 14:25 | 15:12 | 0.12 | 0.47
0.05